## Project Planner
Big Open Source Sister
ACTIVITY	ACTIVITY	PERIODS (week)
		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22
Mentors selection	Create mentors application form
	Mentors applying period
	Select Mentors
	Communicate application results
Mentor training	Prepare mentoring material
	FOSS training
	BOSS introduction
	One-on-one training
	Chatbot framework training
Participants selection	Create participans application form
	Participants applying period
	Select participants
	Communicate application results
Determine content schedule	Assign responsible mentors to review and lead the live session
	Review the Program Roadmap
	Review self-assessment questionnaire
	Weekly mentors planning
	Introduction to FOSS
	What is Linux and how to install
	Code versioning with git
	Contributing to open repositories
	How to make good issues and PR's
	Basic chatbot concepts
Content	RASA boilerplate project architecture
	RASA actions
	Python basics
	RASA slots
	RASA Custom action
	Debugging techniques
	Frequent Asked Questions
Mentee's personal development	Getting to know each other(Mentors and mentees)
	Create Profile Repository
	Train git concepts with GitTrainingWall repository
	Create an initial bot adapting Rasa Boilerplate in a personal fork
	Run Rasa Boilerplate's makefile
	Create an action in their Rasa Boilerplate personal fork
	Create a custom action integrated with an API in their Rasa Boilerplate personal fork
FOSS contribution	Basic contribution to an open repository
	Contribution with Rasa Boilerplate repository
Talk like a Boss	Plan and write script
	Host interviews
Mental health week	Break
Checkpoint	Mentors-only checkpoint
	Mentors and mentees checkpoint
One-on-One	Weekly meeting with mentees
Mentorship ending	Discussion between mentors and organizers about positive and negative aspects of this run
	Closing party with mentors and mentees