## Project Planner
Big Open Source Sister
ACTIVITY	ACTIVITY	PERIODS (week)
		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22
Mentors selection	Create mentors application form
	Mentors applying period
	Select Mentors
	Communicate application results
Mentor training	Prepare mentoring material
	FOSS training
	BOSS introduction
	One-on-one training
	Project framework training
Participants selection	Create participans application form
	Participants applying period
	Select participants
	Communicate application results
Determine content schedule	Assign responsible mentors to review and lead the live session (acho que não precisa mais desse)
	Review the Program Roadmap
	Review self-assessment questionnaire
	Weekly mentors planning
Content	Welcome to BOSS
	Overcoming Technical and non technical challenges of contributing to Open Source
	Community Bonding
	What's next? Finding your favorite OSS project to contribute
FOSS contribution	Basic contribution to an open source repository
	Contribution to main project
Talk like a Boss	Plan and write script
	Host interviews
Mental health week	Break
One-on-One	Weekly meeting with mentees
Mentorship ending	Discussion between mentors and organizers about positive and negative aspects of this run
	Closing party with mentors and mentees